## DailyBoard
To Do | In Progress | Completed | Comments | Important Points
As a PhD Intern, first I would complete the 2 courses recommended. Then, I would like to understand and explore the kaggle competion, so that I have clear understaing of the project . Tasks for data exploration: 1) Download 2) Read the data description 3) Check the basic data structure 4) Analyze the variables and their distributions 5) Basic text statistics (length) 6) Visualization. Story points: 2 Start Date: 22/07/2024 End Date: 23/07/2024 | I have almost finished the courses and doing all the tasks mentioned in "To Do" list in parallel | 1. Course:Generative AI for everyone 2. Course: Genrative AI with LLMs 3. Kaggle project compelete understanding (Completed all mentioned in "To Do") | How the dataset generated: 1. By GPT 3.5 2. Given snippets of text on a range of scientific topics(wikipedia) to GPT 3. GPT wrote MCQs with known answers 4. GPT filtered out easy ones Data Description: 1. Size = 200 2. Possibility of distributional shift (from training set to hidden test set) 3. 5 choices for each question and target (answers), so columns = 7 4. Test data is same as training without labels Task: predict the top three most probable answers (in-case we get hiiden data), otherwise just predict the topmost target | Distribution of target variable: Categories: 5 (A,B,C,D,E) Frequency in Descending: B=48, C=44, D=38, A=37, E=33
As a PhD Intern, I would like to create a design of how to solve the kaggle competion project, so that I have a plan for solution implementation Story points: 2 Start Date: 24/07/2024 End Date: 25/07/2024 Output: Diagram for implementation plan | I am taking literature review on different techniques that can be used to solve the problem proposed in the project, to be able to design the solution | I have completed the workflow for solution implememtation | #VALUE! | Main goal is to use the prompt engineering (using llama or GPT models) and RAG framework
As a PhD Intern, I would take the short course on vector databases as recommended and then write the code for the kaggle competion, so that I can implement my solution Story points: 5 Start Date: 26/07/2024 End Date: 01/08/2024 Output: Metric score achieved | I have finished the course to date 29/07, accessed GPT through python, trying to use Llama, trying to use zero-shot inference from gpt-3.5-turbo, improving the performance(using few shots inference), using gpt-4o-mini for more improvements with the same techniques | 1. I have finished the short course on vector databases 2. First attempt to use gpt-3.5-turbo for kaggle project using zero shot inference in in-context learning and got 64% performance 3. Completed few shots prompt engineering and improved the performance to 71% 4. Used gpt-4o-mini and zero shot with improved prompts, got 81.5% performance | 1. LLaMa needed permission to access. I applied and got a URL code, but the procedure next to use it was complicated, so got stuck. Needed some installations, execution of a file from github, etc. Also unable to connect to Hugging face. Blockers!!!!!! 2. From gpt-3.5-turbo, got approx. 64% accuracy. Took 68m13.9s to completing the task, max calls per min were 3 so if calls finished in < 62s (margin of 2s) waited until it finished 62s to attempt next call, and in case of getting error max tries were 5 and wait of 2 mins before the next retry. Did not split the data as I was not fine tunning. 3. Token count was very small for each call, so no problems regarding that. 4. Incorrectly predicted: A: 10.8%, B: 16.7%, C: 34.1%, D: 39.5%, E: 30.3% | 1. Focus is to improve the performane of the model 2. Possibilities: change temperature?, changing prompts, 1-shot/few-shot (examples from where?), or RAG(which data relevant?) 3. Figured out the correct ways to improve the performance (decided to use few shots prmpt engineering); temperature must be 0 to get deterministic results, saved 10 samples from the dataset for few shots based on the different domains those samples belong to (used gpt-3.5-turbo for this task) . 4. Got the best results with gpt-4o-mini on improved prompts with zero shot but still I am certain that performance will increase with few techniques I menitoned in attached pdf.
As a PhD Intern, I would like to review top solutions on kaggle, so that I can identify the gaps on my solution Story points: 2 Start Date: 02/08/2024 End Date: 06/08/2024 Output: Document containing gaps in implementation and top strategies used (minumum 3) using top solutions on Kaggle | 1. I am reading the top solutions from kaggle to find the gaps 2. Looking for atleast 3 strategies that could be implemented for improvements in my work | Looked at top 5 solutions, and took out the strategies used in the topmost solution in comments section, and some extra strategies in the important points | 1. Context retrieval from wikipedia articles; used 300 combinations of Retrieval + LLM models + different wikipedia dumps for contexts. 2. Used publicly shared datasets and 6k STEM questions dataset. 3. Trained 6 LLM models with synthetic multi-choice samples and generated contexts using RAG. 4. Fine-tuned 7B & 13B LLMs using LORA. Best performing: Llama-2-7b, Mistral-7B-v0.1, xgen-7b-8k-base, and Llama-2-13b | 1. Knowledge database: Used Hugging face dataset, used full wikipedia indexing to retrieve information. Reranker model: deberta-v3-base; predicts the best context for a given question/answer pair. Used Deberta and Mistral based models. 2. Used BM-25 based sparse retrieval, and also dense retrieval methods(sentence/paragraph wise). Generated additional QA dataset using ChatGPT 3.5. Used Mistral 7B and Llama-70B models. Employed QLoRA for fine tunning. 3. Retrieval competition, rather than a model training competition
As a PhD Intern, I would like to integrate top stratgeies in my solution, so that I can improve upon my initial metrics achieved, and start looking into streamlit for the main project. Story points: 2 Start Date: 07/08/2024 End Date: 08/08/2028 Output: Metric score achieved | I am reading about streamlit and langchain, and trying to improve accuracy as well | 1. My initial score via gpt-3.5-turbo gave 64% performance, which I increased with prompt engineering (by changing prompts, and using few shots with different ways) to 71% 2. Then, I changed my model to gpt-4o-mini to enhance the performance to 81.5%, which can still be improved if I keep doing prompt engineering improving my ways. Finally with gpt-4-turbo, improved to 86% with temp = 0.87432. 3. Used ensemble method with majority voting for these 3 gpt models, and got 84% accuracy which is less than achieved with gpt-4-turbo | 1. Our main goal for this project was to practice prompt engineering (specifically using GPT models) 2. The kaggle solutions focused entirely on RAG and fine tunning of different models, and using hugging face/publicaly available datasets or generating datasets for trainings and validations. | 1. Streamlit is an open-source Python library designed for creating interactive, web-based applications specifically for data science and machine learning projects. 2. It is compatible with the majority of Python libraries (e.g. pandas, matplotlib, seaborn, plotly, Keras, PyTorch, SymPy(latex)). 3. Streamlit is used for creating and deploying web intefaces 5. What's the purpose of using streamlit in our project? To generate an application using RAG through streamlit, langchain, & pinecone? LangChain is a framework designed to simplify the development of applications using LLMs. It provides utilities to integrate with various LLMs, such as OpenAI GPT models ,facilitates the creation and management of prompts, includes features for document loading, splitting, retrievals, & generations. In short, provides a framework to modularize and chain different components and tasks related to LLMs, focusing on the backend logic rather than the user interface.

## Retrospective1
2024-07-31
What did we do well | What can be done better | Action Items

## Retrospective2
2024-08-09
What did we do well | What can be done better | Action Items